## Sheet1
ProjectID | ProjectName | County | SubCountyID | ContractorID | StartDate | PlannedEndDate | RevisedEndDate | ActualEndDate | PlannedUnits | CompletedUnits | ProgressPercentage | BudgetAllocated | BudgetSpent | Status | Scenario
1 | Housing_Project_1 | Nakuru | 5 | 1 | 2024-04-11 | 2025-12-14 |  |  | 110 | 15 | 14 | 32575562 | 24530915.63 | Delayed | delayed
2 | Housing_Project_2 | Nakuru | 3 | 1 | 2024-05-11 | 2025-05-29 | 2026-01-27 | 2026-01-07 | 509 | 509 | 100 | 49587039 | 45344685.95 | Completed | completed_after_extension
3 | Housing_Project_3 | Nairobi | 3 | 2 | 2023-12-23 | 2025-08-26 |  | 2025-08-16 | 364 | 364 | 100 | 40868105 | 30680488.81 | Completed | completed_on_time
4 | Housing_Project_4 | Nairobi | 1 | 1 | 2024-11-12 | 2025-08-18 | 2026-01-16 |  | 432 | 406 | 94 | 101030736 | 79325758.13 | Ongoing | ongoing_extension
5 | Housing_Project_5 | Uasin Gishu | 5 | 4 | 2024-06-05 | 2025-04-08 |  |  | 160 | 92 | 58 | 94093639 | 75766531.36 | Ongoing | ongoing_on_track
6 | Housing_Project_6 | Kisumu | 2 | 5 | 2025-05-24 | 2026-01-30 |  |  | 313 | 46 | 15 | 58840994 | 75884585.91 | Ongoing | ongoing_on_track
7 | Housing_Project_7 | Nairobi | 3 | 4 | 2025-02-25 | 2026-12-01 |  |  | 246 | 137 | 56 | 69684848 | 59140798.12 | Ongoing | ongoing_on_track
8 | Housing_Project_8 | Uasin Gishu | 3 | 1 | 2024-03-23 | 2025-03-13 |  | 2025-02-24 | 330 | 330 | 100 | 41931511 | 38727195.01 | Completed | completed_on_time
9 | Housing_Project_9 | Uasin Gishu | 3 | 5 | 2025-04-26 | 2026-09-20 | 2027-06-22 |  | 137 | 121 | 89 | 50742311 | 59635500.56 | Ongoing | ongoing_extension
10 | Housing_Project_10 | Mombasa | 4 | 3 | 2025-09-30 | 2026-10-31 |  | 2026-10-02 | 402 | 402 | 100 | 48538251 | 51392643.12 | Completed | completed_on_time
11 | Housing_Project_11 | Uasin Gishu | 3 | 4 | 2025-07-13 | 2026-10-07 |  |  | 332 | 89 | 27 | 119990728 | 119145716.57 | Ongoing | ongoing_on_track
12 | Housing_Project_12 | Uasin Gishu | 1 | 5 | 2024-09-24 | 2026-11-10 | 2027-04-21 | 2027-04-10 | 304 | 304 | 100 | 38566572 | 36895420.94 | Completed | completed_after_extension
13 | Housing_Project_13 | Nairobi | 4 | 1 | 2025-07-03 | 2026-06-11 |  | 2026-05-17 | 512 | 512 | 100 | 100048665 | 64478302.53 | Completed | completed_on_time
14 | Housing_Project_14 | Nakuru | 5 | 4 | 2024-06-13 | 2025-08-24 |  |  | 91 | 72 | 80 | 111306093 | 122938166.7 | Ongoing | ongoing_on_track
15 | Housing_Project_15 | Kisumu | 3 | 3 | 2025-08-14 | 2026-12-07 |  |  | 241 | 156 | 65 | 80897765 | 48722436.17 | Ongoing | ongoing_on_track
16 | Housing_Project_16 | Nakuru | 2 | 2 | 2024-07-05 | 2025-04-19 |  |  | 385 | 346 | 90 | 105758349 | 101037721.17 | Ongoing | ongoing_on_track
17 | Housing_Project_17 | Kiambu | 1 | 3 | 2023-10-18 | 2024-09-27 |  |  | 80 | 63 | 79 | 100388981 | 83012575.97 | Ongoing | ongoing_on_track
18 | Housing_Project_18 | Nairobi | 1 | 3 | 2023-06-21 | 2024-10-27 |  |  | 139 | 55 | 40 | 52329237 | 63559442.88 | Delayed | delayed
19 | Housing_Project_19 | Nairobi | 5 | 4 | 2023-08-24 | 2024-04-30 |  |  | 208 | 162 | 78 | 37232410 | 39534325.19 | Delayed | delayed
20 | Housing_Project_20 | Kiambu | 3 | 3 | 2024-06-14 | 2026-02-17 |  |  | 285 | 105 | 37 | 115690391 | 94658040.34 | Ongoing | ongoing_on_track
21 | Housing_Project_21 | Mombasa | 5 | 5 | 2024-08-31 | 2025-06-30 | 2025-10-31 |  | 145 | 78 | 54 | 65377076 | 40188856.49 | Ongoing | ongoing_extension
22 | Housing_Project_22 | Kiambu | 1 | 5 | 2025-04-25 | 2025-10-29 |  |  | 140 | 26 | 19 | 50728046 | 32830188.46 | Ongoing | ongoing_on_track
23 | Housing_Project_23 | Kisumu | 5 | 1 | 2024-06-28 | 2025-08-25 |  |  | 577 | 259 | 45 | 48754377 | 47655636.27 | Ongoing | ongoing_on_track
24 | Housing_Project_24 | Nakuru | 4 | 4 | 2025-04-02 | 2027-01-26 |  |  | 274 | 169 | 62 | 32660194 | 21812161.84 | Delayed | delayed
25 | Housing_Project_25 | Kisumu | 3 | 4 | 2024-10-12 | 2026-08-01 |  |  | 180 | 28 | 16 | 28135295 | 24810684.98 | Delayed | delayed
26 | Housing_Project_26 | Nairobi | 3 | 2 | 2025-05-24 | 2026-06-02 |  | 2026-05-16 | 539 | 539 | 100 | 38814949 | 34751689.43 | Completed | completed_on_time
27 | Housing_Project_27 | Mombasa | 5 | 2 | 2023-06-25 | 2024-03-08 |  |  | 180 | 118 | 66 | 26789850 | 28303514.72 | Ongoing | ongoing_on_track
28 | Housing_Project_28 | Nairobi | 4 | 1 | 2023-05-03 | 2024-06-28 |  |  | 496 | 153 | 31 | 85181648 | 79811021.13 | Delayed | delayed
29 | Housing_Project_29 | Nairobi | 5 | 2 | 2024-11-13 | 2025-05-14 | 2025-10-20 |  | 545 | 305 | 56 | 58285503 | 52229944.67 | Ongoing | ongoing_extension
30 | Housing_Project_30 | Uasin Gishu | 5 | 4 | 2025-07-01 | 2026-07-10 |  |  | 302 | 141 | 47 | 27849494 | 28000611.02 | Ongoing | ongoing_on_track
31 | Housing_Project_31 | Nairobi | 5 | 3 | 2025-10-09 | 2026-05-28 | 2026-12-23 |  | 594 | 415 | 70 | 91286543 | 64831968.44 | Ongoing | ongoing_extension
32 | Housing_Project_32 | Nairobi | 5 | 2 | 2025-09-27 | 2027-11-25 |  |  | 320 | 57 | 18 | 74193837 | 50742695.73 | Ongoing | ongoing_on_track
33 | Housing_Project_33 | Kiambu | 5 | 5 | 2024-04-07 | 2024-11-13 |  |  | 163 | 145 | 89 | 76267415 | 80855755.36 | Ongoing | ongoing_on_track
34 | Housing_Project_34 | Nakuru | 2 | 3 | 2023-04-24 | 2024-07-14 | 2024-11-03 | 2024-10-13 | 401 | 401 | 100 | 52035886 | 40896572.15 | Completed | completed_after_extension
35 | Housing_Project_35 | Uasin Gishu | 5 | 3 | 2024-08-25 | 2026-01-10 | 2026-11-03 | 2026-10-10 | 154 | 154 | 100 | 21250299 | 19567272.47 | Completed | completed_after_extension
36 | Housing_Project_36 | Nairobi | 1 | 1 | 2024-06-04 | 2025-07-07 |  | 2025-06-21 | 351 | 351 | 100 | 37778019 | 47346494.76 | Completed | completed_on_time
37 | Housing_Project_37 | Kiambu | 5 | 3 | 2025-02-18 | 2026-01-25 |  |  | 389 | 256 | 66 | 102097999 | 131573417.4 | Ongoing | ongoing_on_track
38 | Housing_Project_38 | Nairobi | 5 | 5 | 2025-02-03 | 2025-11-16 |  |  | 350 | 94 | 27 | 35492573 | 43400279.04 | Ongoing | ongoing_on_track
39 | Housing_Project_39 | Kiambu | 3 | 3 | 2025-02-21 | 2027-05-01 | 2027-08-22 |  | 431 | 366 | 85 | 47326368 | 51171540.28 | Ongoing | ongoing_extension
40 | Housing_Project_40 | Nakuru | 3 | 4 | 2025-03-24 | 2025-11-11 |  |  | 513 | 107 | 21 | 57135391 | 36044474.66 | Delayed | delayed
41 | Housing_Project_41 | Kiambu | 1 | 3 | 2025-06-24 | 2027-03-18 |  |  | 517 | 413 | 80 | 95283645 | 57815141.96 | Ongoing | ongoing_on_track
42 | Housing_Project_42 | Uasin Gishu | 3 | 2 | 2024-05-27 | 2024-12-29 |  |  | 231 | 131 | 57 | 77684996 | 53541420.86 | Delayed | delayed
43 | Housing_Project_43 | Kisumu | 5 | 1 | 2023-05-31 | 2024-11-27 |  |  | 335 | 120 | 36 | 109514287 | 73588731.33 | Ongoing | ongoing_on_track
44 | Housing_Project_44 | Mombasa | 2 | 5 | 2023-10-31 | 2024-10-03 | 2025-07-26 | 2025-06-27 | 322 | 322 | 100 | 41810617 | 53657413.79 | Completed | completed_after_extension
45 | Housing_Project_45 | Mombasa | 1 | 1 | 2025-06-06 | 2026-11-08 |  |  | 334 | 207 | 62 | 55810056 | 39705421.97 | Ongoing | ongoing_on_track
46 | Housing_Project_46 | Mombasa | 2 | 1 | 2023-07-11 | 2025-05-02 | 2025-08-26 |  | 551 | 286 | 52 | 66930359 | 54456789.42 | Ongoing | ongoing_extension
47 | Housing_Project_47 | Kiambu | 3 | 1 | 2024-01-31 | 2025-02-11 |  |  | 416 | 253 | 61 | 57393469 | 69161831.05 | Ongoing | ongoing_on_track
48 | Housing_Project_48 | Kisumu | 3 | 5 | 2024-10-23 | 2026-10-22 |  |  | 108 | 56 | 52 | 35480907 | 43071227.02 | Delayed | delayed
49 | Housing_Project_49 | Kiambu | 3 | 5 | 2023-03-27 | 2024-06-20 |  |  | 191 | 26 | 14 | 100070438 | 90483152.76 | Delayed | delayed
50 | Housing_Project_50 | Mombasa | 4 | 5 | 2024-07-01 | 2025-04-25 |  |  | 274 | 161 | 59 | 54188276 | 34196626.42 | Ongoing | ongoing_on_track
51 | Housing_Project_51 | Nairobi | 3 | 5 | 2023-05-04 | 2025-05-04 | 2025-12-25 | 2025-12-02 | 281 | 281 | 100 | 68884978 | 62127925.12 | Completed | completed_after_extension
52 | Housing_Project_52 | Nakuru | 4 | 3 | 2024-01-27 | 2024-11-29 |  | 2024-11-06 | 387 | 387 | 100 | 88064830 | 71904868.84 | Completed | completed_on_time
53 | Housing_Project_53 | Kisumu | 4 | 4 | 2023-12-24 | 2025-04-19 | 2025-11-06 | 2025-11-02 | 276 | 276 | 100 | 76431351 | 81433829.08 | Completed | completed_after_extension
54 | Housing_Project_54 | Uasin Gishu | 3 | 2 | 2024-03-16 | 2026-04-17 |  | 2026-04-08 | 495 | 495 | 100 | 93542887 | 110718073.71 | Completed | completed_on_time
55 | Housing_Project_55 | Kisumu | 2 | 2 | 2024-09-22 | 2026-11-04 | 2027-06-07 |  | 409 | 331 | 81 | 82409658 | 74930998.99 | Ongoing | ongoing_extension
56 | Housing_Project_56 | Nakuru | 5 | 4 | 2023-09-16 | 2024-09-03 | 2025-04-19 | 2025-04-17 | 370 | 370 | 100 | 89182797 | 94952717.54 | Completed | completed_after_extension
57 | Housing_Project_57 | Kisumu | 1 | 1 | 2023-08-21 | 2024-10-14 |  |  | 310 | 151 | 49 | 46726767 | 32855822.18 | Ongoing | ongoing_on_track
58 | Housing_Project_58 | Kiambu | 4 | 4 | 2024-03-21 | 2024-11-30 |  |  | 504 | 342 | 68 | 104525678 | 104836080.55 | Ongoing | ongoing_on_track
59 | Housing_Project_59 | Mombasa | 5 | 4 | 2025-04-01 | 2026-02-26 |  |  | 189 | 18 | 10 | 77062156 | 58042352.48 | Ongoing | ongoing_on_track
60 | Housing_Project_60 | Mombasa | 5 | 1 | 2024-05-15 | 2025-07-24 |  |  | 547 | 136 | 25 | 37896471 | 43997485.3 | Ongoing | ongoing_on_track
61 | Housing_Project_61 | Nakuru | 5 | 5 | 2025-01-16 | 2026-10-11 |  |  | 596 | 524 | 88 | 77276174 | 91293949.77 | Delayed | delayed
62 | Housing_Project_62 | Mombasa | 3 | 2 | 2023-11-06 | 2025-09-02 |  |  | 345 | 231 | 67 | 53183955 | 63177434.02 | Ongoing | ongoing_on_track
63 | Housing_Project_63 | Nakuru | 2 | 4 | 2024-03-05 | 2025-05-03 |  | 2025-04-25 | 530 | 530 | 100 | 30399639 | 33423837.76 | Completed | completed_on_time
64 | Housing_Project_64 | Kisumu | 2 | 3 | 2025-01-13 | 2027-01-16 |  |  | 221 | 44 | 20 | 40244148 | 30661333.65 | Delayed | delayed
65 | Housing_Project_65 | Uasin Gishu | 1 | 2 | 2025-10-02 | 2027-05-29 |  |  | 418 | 259 | 62 | 92828034 | 85972406.35 | Ongoing | ongoing_on_track
66 | Housing_Project_66 | Kiambu | 3 | 4 | 2024-11-03 | 2026-12-21 |  |  | 469 | 56 | 12 | 84019136 | 50758250.29 | Delayed | delayed
67 | Housing_Project_67 | Kisumu | 4 | 4 | 2023-07-17 | 2025-03-17 |  |  | 305 | 237 | 78 | 85529051 | 64454277.52 | Ongoing | ongoing_on_track
68 | Housing_Project_68 | Mombasa | 4 | 1 | 2024-11-03 | 2026-04-11 |  | 2026-03-21 | 494 | 494 | 100 | 117197979 | 83858823.66 | Completed | completed_on_time
69 | Housing_Project_69 | Kiambu | 2 | 5 | 2024-06-08 | 2025-01-01 |  |  | 107 | 64 | 60 | 31267237 | 32828246.1 | Ongoing | ongoing_on_track
70 | Housing_Project_70 | Mombasa | 4 | 2 | 2025-10-16 | 2027-01-05 | 2027-06-11 | 2027-06-01 | 296 | 296 | 100 | 81028710 | 67155951.76 | Completed | completed_after_extension
71 | Housing_Project_71 | Kisumu | 3 | 4 | 2025-03-23 | 2025-12-11 |  | 2025-11-26 | 99 | 99 | 100 | 92399599 | 58808641.92 | Completed | completed_on_time
72 | Housing_Project_72 | Kiambu | 5 | 1 | 2023-09-29 | 2024-05-07 |  |  | 333 | 43 | 13 | 46757737 | 55522951.37 | Ongoing | ongoing_on_track
73 | Housing_Project_73 | Kiambu | 3 | 2 | 2025-07-30 | 2027-05-25 |  |  | 303 | 72 | 24 | 82415804 | 89802359.98 | Ongoing | ongoing_on_track
74 | Housing_Project_74 | Kiambu | 1 | 5 | 2024-03-25 | 2025-01-16 |  | 2024-12-23 | 247 | 247 | 100 | 61746937 | 41720498.88 | Completed | completed_on_time
75 | Housing_Project_75 | Kisumu | 2 | 5 | 2024-01-13 | 2025-07-30 |  | 2025-07-18 | 283 | 283 | 100 | 30200074 | 30637023.86 | Completed | completed_on_time
76 | Housing_Project_76 | Nairobi | 3 | 3 | 2023-07-20 | 2025-09-21 |  | 2025-08-27 | 203 | 203 | 100 | 95958181 | 110145093.56 | Completed | completed_on_time
77 | Housing_Project_77 | Nakuru | 4 | 4 | 2024-01-29 | 2025-08-10 |  | 2025-08-08 | 598 | 598 | 100 | 106911784 | 89684213.96 | Completed | completed_on_time
78 | Housing_Project_78 | Mombasa | 5 | 1 | 2024-09-19 | 2026-03-23 |  |  | 236 | 160 | 68 | 78450095 | 56742629.93 | Ongoing | ongoing_on_track
79 | Housing_Project_79 | Uasin Gishu | 5 | 3 | 2024-03-16 | 2026-03-17 |  |  | 556 | 394 | 71 | 78461818 | 92429137.24 | Delayed | delayed
80 | Housing_Project_80 | Kisumu | 4 | 3 | 2023-07-18 | 2024-09-21 |  |  | 365 | 76 | 21 | 80505620 | 62046036.16 | Ongoing | ongoing_on_track
81 | Housing_Project_81 | Nakuru | 2 | 5 | 2024-01-22 | 2025-08-12 |  | 2025-08-02 | 109 | 109 | 100 | 86344695 | 103239501.18 | Completed | completed_on_time
82 | Housing_Project_82 | Mombasa | 2 | 2 | 2024-12-08 | 2026-02-25 | 2026-07-22 |  | 362 | 206 | 57 | 94597009 | 57430390.94 | Ongoing | ongoing_extension
83 | Housing_Project_83 | Nairobi | 4 | 2 | 2023-11-30 | 2025-07-18 |  |  | 326 | 234 | 72 | 112692016 | 105171534.32 | Ongoing | ongoing_on_track
84 | Housing_Project_84 | Mombasa | 5 | 1 | 2025-09-02 | 2026-12-27 |  |  | 494 | 187 | 38 | 112850100 | 86929968.45 | Ongoing | ongoing_on_track
85 | Housing_Project_85 | Kisumu | 4 | 4 | 2024-05-19 | 2026-05-12 |  |  | 515 | 278 | 54 | 93871890 | 78059536.98 | Ongoing | ongoing_on_track
86 | Housing_Project_86 | Kisumu | 5 | 3 | 2025-03-24 | 2026-05-14 |  |  | 277 | 69 | 25 | 62352128 | 42629421.57 | Ongoing | ongoing_on_track
87 | Housing_Project_87 | Uasin Gishu | 5 | 2 | 2025-05-24 | 2026-06-29 |  | 2026-06-06 | 575 | 575 | 100 | 57111151 | 63234008.99 | Completed | completed_on_time
88 | Housing_Project_88 | Nakuru | 5 | 3 | 2025-08-26 | 2026-09-08 | 2027-01-21 |  | 449 | 242 | 54 | 44084236 | 35778206.6 | Ongoing | ongoing_extension
89 | Housing_Project_89 | Kiambu | 4 | 3 | 2025-10-21 | 2026-06-13 |  | 2026-05-27 | 379 | 379 | 100 | 113605777 | 143241290.17 | Completed | completed_on_time
90 | Housing_Project_90 | Nairobi | 1 | 1 | 2024-04-28 | 2025-08-12 |  |  | 570 | 399 | 70 | 79118721 | 66340584.93 | Delayed | delayed
91 | Housing_Project_91 | Kisumu | 1 | 4 | 2025-08-12 | 2026-04-15 |  |  | 583 | 355 | 61 | 29943140 | 30060361.69 | Ongoing | ongoing_on_track
92 | Housing_Project_92 | Kiambu | 1 | 2 | 2023-08-29 | 2025-09-23 |  | 2025-08-24 | 391 | 391 | 100 | 31432787 | 40728803.85 | Completed | completed_on_time
93 | Housing_Project_93 | Nakuru | 4 | 4 | 2024-03-26 | 2026-05-25 |  | 2026-04-30 | 311 | 311 | 100 | 90138498 | 78083791.56 | Completed | completed_on_time
94 | Housing_Project_94 | Kisumu | 1 | 5 | 2024-09-23 | 2026-01-28 | 2026-08-21 |  | 141 | 111 | 79 | 101823275 | 129526959.05 | Ongoing | ongoing_extension
95 | Housing_Project_95 | Kiambu | 2 | 2 | 2025-03-11 | 2025-11-29 |  | 2025-11-24 | 325 | 325 | 100 | 43328859 | 42739351.32 | Completed | completed_on_time
96 | Housing_Project_96 | Nairobi | 3 | 4 | 2024-09-01 | 2026-10-29 |  |  | 378 | 264 | 70 | 24380847 | 18579018.86 | Delayed | delayed
97 | Housing_Project_97 | Uasin Gishu | 2 | 4 | 2025-09-25 | 2026-11-18 |  |  | 282 | 121 | 43 | 77061186 | 52428070.19 | Delayed | delayed
98 | Housing_Project_98 | Uasin Gishu | 3 | 2 | 2023-05-21 | 2024-08-15 |  |  | 153 | 42 | 28 | 28004482 | 20055296.43 | Delayed | delayed
99 | Housing_Project_99 | Nakuru | 4 | 5 | 2023-05-08 | 2024-08-25 |  |  | 207 | 136 | 66 | 82907576 | 89712181.63 | Ongoing | ongoing_on_track
100 | Housing_Project_100 | Kisumu | 4 | 5 | 2024-06-02 | 2026-04-18 |  |  | 162 | 106 | 66 | 100267122 | 62957981.48 | Ongoing | ongoing_on_track
101 | Housing_Project_101 | Uasin Gishu | 5 | 3 | 2024-03-28 | 2025-06-07 |  |  | 173 | 22 | 13 | 50725714 | 64590967.62 | Ongoing | ongoing_on_track
102 | Housing_Project_102 | Nakuru | 4 | 1 | 2023-10-15 | 2025-01-12 | 2025-08-07 |  | 259 | 108 | 42 | 83149551 | 80095857.85 | Ongoing | ongoing_extension
103 | Housing_Project_103 | Kisumu | 3 | 2 | 2024-04-16 | 2026-01-02 |  |  | 173 | 124 | 72 | 83083727 | 70087167.19 | Ongoing | ongoing_on_track
104 | Housing_Project_104 | Kisumu | 4 | 1 | 2023-07-12 | 2024-06-20 |  |  | 501 | 260 | 52 | 113103304 | 107089410.71 | Delayed | delayed
105 | Housing_Project_105 | Nakuru | 4 | 1 | 2024-08-28 | 2025-05-25 | 2025-10-12 | 2025-10-04 | 411 | 411 | 100 | 35558733 | 45484217.56 | Completed | completed_after_extension
106 | Housing_Project_106 | Nakuru | 3 | 1 | 2024-02-02 | 2026-02-06 |  |  | 503 | 347 | 69 | 27275149 | 19946528.64 | Ongoing | ongoing_on_track
107 | Housing_Project_107 | Nakuru | 3 | 4 | 2024-03-06 | 2025-11-28 |  |  | 288 | 46 | 16 | 55843681 | 54975521.03 | Delayed | delayed
108 | Housing_Project_108 | Mombasa | 5 | 4 | 2025-08-04 | 2026-03-01 |  | 2026-02-09 | 325 | 325 | 100 | 115265438 | 81938132.69 | Completed | completed_on_time
109 | Housing_Project_109 | Nairobi | 2 | 5 | 2024-10-15 | 2025-07-17 |  |  | 196 | 74 | 38 | 81934487 | 103478547.46 | Ongoing | ongoing_on_track
110 | Housing_Project_110 | Mombasa | 5 | 3 | 2024-07-03 | 2025-10-05 |  |  | 574 | 361 | 63 | 83380266 | 64253803.05 | Ongoing | ongoing_on_track
111 | Housing_Project_111 | Kiambu | 4 | 4 | 2025-05-25 | 2027-07-27 |  |  | 219 | 164 | 75 | 29369750 | 23301172.01 | Ongoing | ongoing_on_track
112 | Housing_Project_112 | Kisumu | 4 | 5 | 2025-03-08 | 2025-09-06 |  |  | 385 | 177 | 46 | 98777447 | 99364814.12 | Ongoing | ongoing_on_track
113 | Housing_Project_113 | Kiambu | 2 | 4 | 2024-06-03 | 2026-04-09 | 2026-09-04 | 2026-08-25 | 466 | 466 | 100 | 81115319 | 101637217.21 | Completed | completed_after_extension
114 | Housing_Project_114 | Uasin Gishu | 4 | 2 | 2024-04-30 | 2025-11-23 |  | 2025-11-16 | 500 | 500 | 100 | 25858241 | 21274180.71 | Completed | completed_on_time
115 | Housing_Project_115 | Uasin Gishu | 3 | 4 | 2024-11-06 | 2025-10-07 | 2026-04-11 |  | 209 | 87 | 42 | 87416376 | 111521224.29 | Ongoing | ongoing_extension
116 | Housing_Project_116 | Nairobi | 4 | 4 | 2025-08-26 | 2027-08-14 |  | 2027-07-16 | 547 | 547 | 100 | 22059919 | 24391888.02 | Completed | completed_on_time
117 | Housing_Project_117 | Uasin Gishu | 4 | 2 | 2025-09-21 | 2027-07-13 |  | 2027-06-18 | 351 | 351 | 100 | 65440919 | 67815218.96 | Completed | completed_on_time
118 | Housing_Project_118 | Uasin Gishu | 4 | 1 | 2023-07-18 | 2024-12-15 |  |  | 469 | 365 | 78 | 62501540 | 64924063.77 | Ongoing | ongoing_on_track
119 | Housing_Project_119 | Nakuru | 4 | 1 | 2024-03-14 | 2024-11-19 |  | 2024-11-12 | 374 | 374 | 100 | 50532691 | 56734894.44 | Completed | completed_on_time
120 | Housing_Project_120 | Nairobi | 1 | 1 | 2024-09-08 | 2025-08-24 |  |  | 109 | 52 | 48 | 26172803 | 21646537.78 | Delayed | delayed
121 | Housing_Project_121 | Kisumu | 2 | 3 | 2024-11-18 | 2026-08-01 |  | 2026-07-28 | 330 | 330 | 100 | 91291936 | 81107062.93 | Completed | completed_on_time
122 | Housing_Project_122 | Kiambu | 2 | 2 | 2025-09-17 | 2027-04-11 |  | 2027-03-23 | 326 | 326 | 100 | 86795767 | 107538246.41 | Completed | completed_on_time
123 | Housing_Project_123 | Kiambu | 4 | 4 | 2024-02-22 | 2025-05-07 |  |  | 341 | 231 | 68 | 109501846 | 66421432.86 | Ongoing | ongoing_on_track
124 | Housing_Project_124 | Kisumu | 4 | 5 | 2025-06-28 | 2026-03-10 |  |  | 433 | 285 | 66 | 98862539 | 80020127.43 | Ongoing | ongoing_on_track
125 | Housing_Project_125 | Uasin Gishu | 4 | 3 | 2024-08-26 | 2025-12-28 |  |  | 473 | 165 | 35 | 84855088 | 57248103.47 | Ongoing | ongoing_on_track
126 | Housing_Project_126 | Nakuru | 1 | 3 | 2024-04-27 | 2025-08-22 |  |  | 102 | 47 | 47 | 108346110 | 95026474.64 | Delayed | delayed
127 | Housing_Project_127 | Nakuru | 2 | 1 | 2023-05-19 | 2025-07-27 |  | 2025-07-04 | 588 | 588 | 100 | 58412328 | 66766382.38 | Completed | completed_on_time
128 | Housing_Project_128 | Nakuru | 2 | 3 | 2025-04-26 | 2026-05-05 |  | 2026-04-16 | 336 | 336 | 100 | 110968005 | 125272238.77 | Completed | completed_on_time
129 | Housing_Project_129 | Uasin Gishu | 2 | 1 | 2023-05-26 | 2024-01-01 |  |  | 531 | 260 | 49 | 24478111 | 24617676.96 | Ongoing | ongoing_on_track
130 | Housing_Project_130 | Nairobi | 3 | 3 | 2025-01-06 | 2026-09-03 |  |  | 285 | 91 | 32 | 37738187 | 43420009.48 | Delayed | delayed
131 | Housing_Project_131 | Nakuru | 3 | 5 | 2023-05-16 | 2024-08-17 |  |  | 343 | 106 | 31 | 84672520 | 108141105.28 | Delayed | delayed
132 | Housing_Project_132 | Uasin Gishu | 2 | 3 | 2023-09-05 | 2024-06-28 |  |  | 157 | 108 | 69 | 38892086 | 43866618.91 | Ongoing | ongoing_on_track
133 | Housing_Project_133 | Uasin Gishu | 5 | 4 | 2023-03-22 | 2025-04-10 |  |  | 172 | 96 | 56 | 72958901 | 44486183.45 | Ongoing | ongoing_on_track
134 | Housing_Project_134 | Nairobi | 1 | 4 | 2024-11-24 | 2026-02-15 |  |  | 470 | 394 | 84 | 105704631 | 132998023.82 | Ongoing | ongoing_on_track
135 | Housing_Project_135 | Uasin Gishu | 1 | 2 | 2024-08-11 | 2025-03-04 | 2025-10-08 | 2025-09-10 | 415 | 415 | 100 | 101883846 | 76917926.81 | Completed | completed_after_extension
136 | Housing_Project_136 | Uasin Gishu | 1 | 4 | 2023-05-20 | 2024-09-20 |  |  | 199 | 123 | 62 | 38760553 | 24486699.03 | Ongoing | ongoing_on_track
137 | Housing_Project_137 | Kisumu | 5 | 4 | 2025-08-10 | 2026-05-16 |  |  | 218 | 87 | 40 | 72163160 | 66213352.91 | Delayed | delayed
138 | Housing_Project_138 | Mombasa | 4 | 5 | 2023-11-07 | 2024-10-10 |  | 2024-09-12 | 504 | 504 | 100 | 107902129 | 72220529.04 | Completed | completed_on_time
139 | Housing_Project_139 | Nakuru | 2 | 4 | 2023-04-20 | 2024-07-29 |  |  | 459 | 64 | 14 | 49161443 | 44755012.42 | Delayed | delayed
140 | Housing_Project_140 | Kisumu | 2 | 1 | 2024-01-04 | 2025-07-13 | 2026-01-28 | 2025-12-31 | 447 | 447 | 100 | 28126895 | 24715039.35 | Completed | completed_after_extension
141 | Housing_Project_141 | Nairobi | 2 | 4 | 2025-09-04 | 2026-10-06 | 2027-05-18 | 2027-04-28 | 101 | 101 | 100 | 26788532 | 30827069.64 | Completed | completed_after_extension
142 | Housing_Project_142 | Kiambu | 2 | 5 | 2025-05-10 | 2026-01-15 |  |  | 292 | 233 | 80 | 98703005 | 74142336.16 | Ongoing | ongoing_on_track
143 | Housing_Project_143 | Kisumu | 5 | 2 | 2023-09-21 | 2025-11-19 |  |  | 363 | 36 | 10 | 39419691 | 50901429.43 | Delayed | delayed
144 | Housing_Project_144 | Kisumu | 2 | 2 | 2025-08-16 | 2026-03-10 |  |  | 95 | 24 | 26 | 68082464 | 78498350.12 | Ongoing | ongoing_on_track
145 | Housing_Project_145 | Nakuru | 5 | 3 | 2025-11-20 | 2026-11-13 |  |  | 133 | 57 | 43 | 37013243 | 41425319.28 | Ongoing | ongoing_on_track
146 | Housing_Project_146 | Nairobi | 5 | 1 | 2024-08-06 | 2026-05-07 |  |  | 191 | 106 | 56 | 80667140 | 76850542.29 | Ongoing | ongoing_on_track
147 | Housing_Project_147 | Nairobi | 4 | 5 | 2025-02-01 | 2026-11-12 | 2027-06-24 |  | 142 | 58 | 41 | 84287863 | 100564606.27 | Ongoing | ongoing_extension
148 | Housing_Project_148 | Uasin Gishu | 1 | 1 | 2024-07-22 | 2026-04-17 |  |  | 162 | 30 | 19 | 63233116 | 64865048.69 | Delayed | delayed
149 | Housing_Project_149 | Kiambu | 5 | 3 | 2024-03-07 | 2026-04-25 |  |  | 412 | 329 | 80 | 71124122 | 92193891.3 | Ongoing | ongoing_on_track
150 | Housing_Project_150 | Kisumu | 5 | 4 | 2024-07-07 | 2026-09-14 |  |  | 181 | 117 | 65 | 114191239 | 77660302.68 | Ongoing | ongoing_on_track
151 | Housing_Project_151 | Uasin Gishu | 4 | 2 | 2024-09-22 | 2026-06-26 | 2027-04-09 | 2027-04-02 | 503 | 503 | 100 | 65490631 | 77226123.59 | Completed | completed_after_extension
152 | Housing_Project_152 | Mombasa | 4 | 1 | 2025-01-20 | 2026-09-29 |  |  | 341 | 170 | 50 | 70237832 | 89027488.93 | Ongoing | ongoing_on_track
153 | Housing_Project_153 | Nairobi | 3 | 1 | 2023-08-08 | 2024-05-01 |  |  | 522 | 109 | 21 | 32960658 | 36955894.45 | Ongoing | ongoing_on_track
154 | Housing_Project_154 | Kiambu | 3 | 5 | 2025-10-06 | 2027-11-25 |  |  | 417 | 337 | 81 | 109927658 | 75362214.05 | Delayed | delayed
155 | Housing_Project_155 | Uasin Gishu | 5 | 4 | 2023-07-02 | 2024-02-19 | 2024-07-01 | 2024-06-12 | 399 | 399 | 100 | 67197152 | 45191455.28 | Completed | completed_after_extension
156 | Housing_Project_156 | Kiambu | 3 | 2 | 2024-02-03 | 2025-12-07 |  |  | 190 | 72 | 38 | 66991504 | 79837888.13 | Ongoing | ongoing_on_track
157 | Housing_Project_157 | Nairobi | 3 | 3 | 2024-04-28 | 2025-06-13 | 2026-03-06 |  | 106 | 71 | 67 | 101737913 | 127208915.54 | Ongoing | ongoing_extension
158 | Housing_Project_158 | Nairobi | 2 | 2 | 2025-03-02 | 2026-07-11 |  | 2026-06-12 | 427 | 427 | 100 | 67113566 | 40554986.51 | Completed | completed_on_time
159 | Housing_Project_159 | Nakuru | 4 | 4 | 2025-09-26 | 2026-08-17 |  |  | 173 | 22 | 13 | 91200181 | 68454218.92 | Ongoing | ongoing_on_track
160 | Housing_Project_160 | Mombasa | 1 | 3 | 2025-06-28 | 2027-01-07 |  | 2026-12-29 | 412 | 412 | 100 | 96181117 | 97850498.07 | Completed | completed_on_time
161 | Housing_Project_161 | Kiambu | 4 | 2 | 2023-10-26 | 2024-06-12 |  |  | 358 | 71 | 20 | 79473616 | 84508832.64 | Delayed | delayed
162 | Housing_Project_162 | Nakuru | 3 | 4 | 2024-10-08 | 2026-01-10 | 2026-05-05 |  | 196 | 172 | 88 | 66328316 | 59757802.73 | Ongoing | ongoing_extension
163 | Housing_Project_163 | Uasin Gishu | 5 | 5 | 2024-07-26 | 2026-07-15 | 2027-03-02 |  | 126 | 74 | 59 | 49597483 | 43481338.5 | Ongoing | ongoing_extension
164 | Housing_Project_164 | Nairobi | 1 | 1 | 2025-05-11 | 2026-09-11 |  |  | 220 | 81 | 37 | 54295247 | 43578070.64 | Delayed | delayed
165 | Housing_Project_165 | Nairobi | 2 | 4 | 2023-11-03 | 2025-07-15 |  |  | 212 | 67 | 32 | 71030579 | 69099090.17 | Ongoing | ongoing_on_track
166 | Housing_Project_166 | Nakuru | 1 | 5 | 2023-08-06 | 2025-01-29 |  | 2025-01-27 | 486 | 486 | 100 | 119595101 | 75298460.87 | Completed | completed_on_time
167 | Housing_Project_167 | Mombasa | 4 | 1 | 2023-07-08 | 2024-11-19 |  |  | 519 | 430 | 83 | 96960402 | 85625345.02 | Ongoing | ongoing_on_track
168 | Housing_Project_168 | Kisumu | 3 | 1 | 2024-10-18 | 2025-05-07 |  |  | 255 | 130 | 51 | 102963368 | 94939209.44 | Ongoing | ongoing_on_track
169 | Housing_Project_169 | Nairobi | 1 | 4 | 2023-07-26 | 2024-05-09 |  |  | 526 | 215 | 41 | 99036966 | 87183713.99 | Ongoing | ongoing_on_track
170 | Housing_Project_170 | Mombasa | 1 | 3 | 2023-11-04 | 2025-04-14 | 2025-08-08 |  | 252 | 153 | 61 | 30251466 | 28960887.01 | Ongoing | ongoing_extension
171 | Housing_Project_171 | Nakuru | 3 | 5 | 2025-05-22 | 2026-11-10 | 2027-04-08 |  | 231 | 198 | 86 | 51711468 | 34748201.93 | Ongoing | ongoing_extension
172 | Housing_Project_172 | Kiambu | 5 | 2 | 2024-03-30 | 2025-03-01 |  |  | 261 | 49 | 19 | 104281857 | 98638322.86 | Ongoing | ongoing_on_track
173 | Housing_Project_173 | Nakuru | 4 | 4 | 2024-01-09 | 2026-02-05 |  |  | 410 | 377 | 92 | 104183695 | 85565779.71 | Delayed | delayed
174 | Housing_Project_174 | Nairobi | 3 | 4 | 2024-09-10 | 2026-01-13 |  |  | 137 | 61 | 45 | 67236885 | 64220357.27 | Ongoing | ongoing_on_track
175 | Housing_Project_175 | Mombasa | 1 | 4 | 2025-10-29 | 2026-06-24 | 2026-11-25 |  | 373 | 346 | 93 | 30298660 | 31851967.12 | Ongoing | ongoing_extension
176 | Housing_Project_176 | Nakuru | 5 | 5 | 2024-07-05 | 2026-01-29 |  |  | 122 | 84 | 69 | 80362235 | 99354641.37 | Ongoing | ongoing_on_track
177 | Housing_Project_177 | Uasin Gishu | 3 | 2 | 2025-01-11 | 2027-03-21 | 2027-09-18 |  | 234 | 168 | 72 | 28304547 | 25909024.96 | Ongoing | ongoing_extension
178 | Housing_Project_178 | Uasin Gishu | 4 | 1 | 2024-07-08 | 2025-06-29 |  |  | 333 | 49 | 15 | 114975377 | 104217222.04 | Delayed | delayed
179 | Housing_Project_179 | Nakuru | 3 | 5 | 2024-03-22 | 2025-02-27 | 2025-07-30 | 2025-07-19 | 369 | 369 | 100 | 71998170 | 63800355.99 | Completed | completed_after_extension
180 | Housing_Project_180 | Uasin Gishu | 4 | 5 | 2025-10-14 | 2027-03-20 |  |  | 417 | 75 | 18 | 32684373 | 32376298.23 | Ongoing | ongoing_on_track
181 | Housing_Project_181 | Kisumu | 2 | 3 | 2023-11-26 | 2026-01-31 |  |  | 421 | 122 | 29 | 30939011 | 31183975.58 | Ongoing | ongoing_on_track
182 | Housing_Project_182 | Kisumu | 3 | 3 | 2023-03-22 | 2024-10-23 |  |  | 166 | 43 | 26 | 61551377 | 61012522.33 | Ongoing | ongoing_on_track
183 | Housing_Project_183 | Kiambu | 2 | 5 | 2025-09-02 | 2027-05-08 | 2027-11-14 | 2027-11-03 | 98 | 98 | 100 | 68667035 | 56046463.07 | Completed | completed_after_extension
184 | Housing_Project_184 | Kisumu | 1 | 4 | 2025-05-24 | 2026-07-09 |  | 2026-07-05 | 238 | 238 | 100 | 30356922 | 24499689.63 | Completed | completed_on_time
185 | Housing_Project_185 | Nakuru | 4 | 5 | 2023-08-04 | 2025-07-23 |  |  | 424 | 59 | 14 | 102950779 | 71214588.03 | Ongoing | ongoing_on_track
186 | Housing_Project_186 | Kiambu | 2 | 2 | 2025-06-04 | 2026-05-19 | 2027-01-18 |  | 124 | 84 | 68 | 75144509 | 64249275.82 | Ongoing | ongoing_extension
187 | Housing_Project_187 | Mombasa | 4 | 5 | 2025-02-18 | 2026-11-19 |  | 2026-11-12 | 324 | 324 | 100 | 61536077 | 78514966.51 | Completed | completed_on_time
188 | Housing_Project_188 | Kiambu | 4 | 3 | 2024-01-12 | 2026-02-14 | 2026-08-05 |  | 368 | 253 | 69 | 71254050 | 67836326.98 | Ongoing | ongoing_extension
189 | Housing_Project_189 | Kiambu | 3 | 2 | 2023-09-08 | 2025-11-15 |  |  | 336 | 90 | 27 | 27003454 | 28321906.43 | Delayed | delayed
190 | Housing_Project_190 | Nakuru | 3 | 1 | 2023-12-09 | 2025-11-16 |  |  | 371 | 92 | 25 | 31257528 | 35451718.78 | Ongoing | ongoing_on_track
191 | Housing_Project_191 | Mombasa | 1 | 5 | 2025-07-09 | 2027-03-28 |  |  | 307 | 64 | 21 | 80549373 | 98209085.33 | Ongoing | ongoing_on_track
192 | Housing_Project_192 | Mombasa | 3 | 1 | 2024-10-27 | 2026-09-21 |  | 2026-09-10 | 321 | 321 | 100 | 71830338 | 93104167.29 | Completed | completed_on_time
193 | Housing_Project_193 | Kiambu | 3 | 1 | 2025-01-14 | 2025-10-22 | 2026-07-23 | 2026-07-01 | 423 | 423 | 100 | 39602406 | 27575935.92 | Completed | completed_after_extension
194 | Housing_Project_194 | Mombasa | 2 | 2 | 2023-10-21 | 2025-08-11 | 2026-02-01 |  | 85 | 67 | 79 | 30633503 | 18787610.7 | Ongoing | ongoing_extension
195 | Housing_Project_195 | Kiambu | 1 | 5 | 2023-04-19 | 2025-04-08 |  |  | 193 | 123 | 64 | 58668339 | 44960373.56 | Ongoing | ongoing_on_track
196 | Housing_Project_196 | Nairobi | 1 | 2 | 2024-10-03 | 2026-07-13 |  |  | 193 | 34 | 18 | 87085942 | 88628872.37 | Ongoing | ongoing_on_track
197 | Housing_Project_197 | Uasin Gishu | 5 | 5 | 2024-04-27 | 2025-06-28 |  | 2025-06-06 | 227 | 227 | 100 | 59093864 | 53212087.74 | Completed | completed_on_time
198 | Housing_Project_198 | Kisumu | 1 | 2 | 2024-05-01 | 2025-12-28 |  | 2025-12-23 | 167 | 167 | 100 | 90260907 | 115737783.06 | Completed | completed_on_time
199 | Housing_Project_199 | Nakuru | 1 | 5 | 2024-07-05 | 2026-06-04 |  | 2026-05-18 | 100 | 100 | 100 | 72405812 | 87707477.57 | Completed | completed_on_time
200 | Housing_Project_200 | Uasin Gishu | 3 | 4 | 2024-11-19 | 2026-02-01 |  | 2026-01-09 | 96 | 96 | 100 | 67928328 | 78250989.21 | Completed | completed_on_time
201 | Housing_Project_201 | Kiambu | 5 | 1 | 2023-10-08 | 2025-11-21 | 2026-07-27 |  | 420 | 369 | 88 | 37905932 | 23919969.11 | Ongoing | ongoing_extension
202 | Housing_Project_202 | Kisumu | 4 | 2 | 2023-08-09 | 2025-05-25 |  |  | 266 | 188 | 71 | 38099607 | 24542638.16 | Ongoing | ongoing_on_track
203 | Housing_Project_203 | Nairobi | 5 | 3 | 2025-05-14 | 2025-12-24 |  |  | 122 | 42 | 35 | 62358553 | 78157696.41 | Ongoing | ongoing_on_track
204 | Housing_Project_204 | Mombasa | 1 | 5 | 2024-08-09 | 2025-10-22 |  | 2025-10-21 | 275 | 275 | 100 | 58401154 | 49634085.08 | Completed | completed_on_time
205 | Housing_Project_205 | Uasin Gishu | 4 | 3 | 2025-03-02 | 2026-01-03 | 2026-09-24 |  | 527 | 332 | 63 | 73690013 | 82556055.94 | Ongoing | ongoing_extension
206 | Housing_Project_206 | Kisumu | 1 | 2 | 2024-07-16 | 2026-06-05 |  |  | 353 | 201 | 57 | 31087928 | 34475173.1 | Ongoing | ongoing_on_track
207 | Housing_Project_207 | Mombasa | 3 | 5 | 2023-08-17 | 2024-08-15 |  |  | 380 | 300 | 79 | 63112268 | 42399991.46 | Ongoing | ongoing_on_track
208 | Housing_Project_208 | Uasin Gishu | 3 | 3 | 2025-01-27 | 2026-10-25 | 2027-05-27 |  | 516 | 438 | 85 | 42366682 | 45876141.61 | Ongoing | ongoing_extension
209 | Housing_Project_209 | Mombasa | 1 | 1 | 2023-11-23 | 2025-05-17 |  |  | 525 | 462 | 88 | 56850196 | 59557886.55 | Ongoing | ongoing_on_track
210 | Housing_Project_210 | Nairobi | 4 | 4 | 2024-11-29 | 2026-11-04 |  |  | 111 | 33 | 30 | 39163535 | 46763944.16 | Ongoing | ongoing_on_track
211 | Housing_Project_211 | Nairobi | 5 | 2 | 2025-09-29 | 2026-11-24 |  |  | 455 | 418 | 92 | 68607028 | 59550768.66 | Delayed | delayed
212 | Housing_Project_212 | Nairobi | 5 | 5 | 2025-07-02 | 2027-04-03 | 2027-09-04 |  | 534 | 336 | 63 | 30319387 | 30372301.75 | Ongoing | ongoing_extension
213 | Housing_Project_213 | Kisumu | 5 | 4 | 2025-01-19 | 2026-04-29 | 2026-08-30 |  | 106 | 49 | 47 | 118740608 | 86708385.76 | Ongoing | ongoing_extension
214 | Housing_Project_214 | Mombasa | 3 | 5 | 2025-08-08 | 2026-10-30 |  |  | 536 | 230 | 43 | 48799154 | 63314734.58 | Ongoing | ongoing_on_track
215 | Housing_Project_215 | Uasin Gishu | 4 | 4 | 2025-05-16 | 2026-03-17 |  | 2026-03-13 | 155 | 155 | 100 | 80672142 | 58153276.3 | Completed | completed_on_time
216 | Housing_Project_216 | Nairobi | 2 | 3 | 2024-01-23 | 2025-07-11 |  |  | 377 | 67 | 18 | 60259503 | 72067559.64 | Ongoing | ongoing_on_track
217 | Housing_Project_217 | Kisumu | 1 | 5 | 2025-04-21 | 2026-02-19 |  |  | 222 | 77 | 35 | 51774192 | 59709163.82 | Ongoing | ongoing_on_track
218 | Housing_Project_218 | Kisumu | 1 | 5 | 2024-04-29 | 2025-11-07 |  | 2025-10-24 | 212 | 212 | 100 | 102134318 | 124498926.25 | Completed | completed_on_time
219 | Housing_Project_219 | Kisumu | 3 | 4 | 2023-12-03 | 2025-10-03 | 2026-04-15 |  | 499 | 329 | 66 | 97161840 | 63313132.48 | Ongoing | ongoing_extension
220 | Housing_Project_220 | Uasin Gishu | 5 | 1 | 2024-09-02 | 2026-06-21 |  | 2026-05-31 | 432 | 432 | 100 | 37224779 | 45212178.23 | Completed | completed_on_time
221 | Housing_Project_221 | Uasin Gishu | 3 | 5 | 2025-06-03 | 2026-04-11 | 2026-09-28 |  | 136 | 97 | 72 | 36664623 | 35295987.37 | Ongoing | ongoing_extension
222 | Housing_Project_222 | Kiambu | 5 | 2 | 2025-01-10 | 2026-02-24 | 2026-07-22 |  | 370 | 270 | 73 | 30584397 | 23715866.78 | Ongoing | ongoing_extension
223 | Housing_Project_223 | Kisumu | 5 | 2 | 2024-03-06 | 2025-07-09 |  |  | 175 | 154 | 88 | 87454225 | 91712476.08 | Ongoing | ongoing_on_track
224 | Housing_Project_224 | Nakuru | 5 | 2 | 2025-06-14 | 2027-08-22 |  |  | 122 | 64 | 53 | 23808225 | 15638575.4 | Delayed | delayed
225 | Housing_Project_225 | Kisumu | 5 | 2 | 2023-10-13 | 2025-11-16 |  |  | 111 | 69 | 63 | 86845536 | 106151109.07 | Ongoing | ongoing_on_track
226 | Housing_Project_226 | Kisumu | 1 | 3 | 2024-07-30 | 2025-10-03 |  |  | 384 | 234 | 61 | 80873663 | 52655314.91 | Ongoing | ongoing_on_track
227 | Housing_Project_227 | Kiambu | 3 | 4 | 2024-10-07 | 2026-08-13 | 2027-02-07 | 2027-02-01 | 428 | 428 | 100 | 101424562 | 71054811.05 | Completed | completed_after_extension
228 | Housing_Project_228 | Uasin Gishu | 3 | 3 | 2023-03-14 | 2024-10-22 |  |  | 459 | 119 | 26 | 89119463 | 88509516.12 | Delayed | delayed
229 | Housing_Project_229 | Kiambu | 3 | 4 | 2025-08-03 | 2026-10-30 |  | 2026-10-16 | 333 | 333 | 100 | 38908276 | 25981707.75 | Completed | completed_on_time
230 | Housing_Project_230 | Mombasa | 2 | 5 | 2024-10-04 | 2025-12-12 | 2026-09-19 |  | 415 | 207 | 50 | 97535841 | 107756612.04 | Ongoing | ongoing_extension
231 | Housing_Project_231 | Kiambu | 4 | 4 | 2024-06-27 | 2026-04-16 |  | 2026-04-01 | 395 | 395 | 100 | 86755908 | 53461021.36 | Completed | completed_on_time
232 | Housing_Project_232 | Nakuru | 4 | 4 | 2023-03-23 | 2024-05-22 |  |  | 441 | 163 | 37 | 26530784 | 16857083.99 | Delayed | delayed
233 | Housing_Project_233 | Nakuru | 3 | 4 | 2025-02-17 | 2027-02-16 | 2027-04-19 |  | 190 | 178 | 94 | 77838146 | 54000561.01 | Ongoing | ongoing_extension
234 | Housing_Project_234 | Uasin Gishu | 5 | 3 | 2023-10-16 | 2025-05-30 |  |  | 126 | 70 | 56 | 73765155 | 46900651.32 | Delayed | delayed
235 | Housing_Project_235 | Kiambu | 5 | 3 | 2024-05-19 | 2025-09-06 |  |  | 475 | 90 | 19 | 87680031 | 80248978.84 | Ongoing | ongoing_on_track
236 | Housing_Project_236 | Kisumu | 3 | 5 | 2024-01-10 | 2024-11-06 |  | 2024-11-02 | 179 | 179 | 100 | 72868861 | 62757492.99 | Completed | completed_on_time
237 | Housing_Project_237 | Nakuru | 1 | 3 | 2023-10-25 | 2024-09-16 |  |  | 491 | 171 | 35 | 87119320 | 54726478.04 | Ongoing | ongoing_on_track
238 | Housing_Project_238 | Kiambu | 5 | 3 | 2023-09-05 | 2025-07-01 |  |  | 547 | 415 | 76 | 39990477 | 40965539.43 | Ongoing | ongoing_on_track
239 | Housing_Project_239 | Kiambu | 5 | 3 | 2023-04-28 | 2024-09-15 | 2024-12-25 |  | 386 | 250 | 65 | 99688374 | 83285790.15 | Ongoing | ongoing_extension
240 | Housing_Project_240 | Nakuru | 1 | 4 | 2023-12-12 | 2026-01-06 |  |  | 566 | 271 | 48 | 22232974 | 19072567.13 | Ongoing | ongoing_on_track
241 | Housing_Project_241 | Mombasa | 5 | 5 | 2025-01-25 | 2025-08-20 | 2026-03-20 | 2026-03-05 | 351 | 351 | 100 | 107991930 | 123978277.13 | Completed | completed_after_extension
242 | Housing_Project_242 | Nakuru | 5 | 2 | 2023-11-29 | 2024-07-18 | 2025-02-12 | 2025-01-28 | 254 | 254 | 100 | 90361272 | 94004427.84 | Completed | completed_after_extension
243 | Housing_Project_243 | Mombasa | 3 | 2 | 2023-08-18 | 2024-10-19 | 2024-12-26 | 2024-12-08 | 192 | 192 | 100 | 45606639 | 27968552.18 | Completed | completed_after_extension
244 | Housing_Project_244 | Mombasa | 1 | 2 | 2024-10-10 | 2025-11-02 |  |  | 593 | 367 | 62 | 102071195 | 127013788.36 | Delayed | delayed
245 | Housing_Project_245 | Uasin Gishu | 4 | 2 | 2024-06-23 | 2025-07-20 |  |  | 412 | 333 | 81 | 108882576 | 101789931.07 | Ongoing | ongoing_on_track
246 | Housing_Project_246 | Kisumu | 3 | 2 | 2024-08-23 | 2026-08-18 | 2027-01-12 | 2026-12-26 | 442 | 442 | 100 | 110713544 | 126256933.85 | Completed | completed_after_extension
247 | Housing_Project_247 | Nakuru | 3 | 4 | 2025-05-24 | 2026-07-30 |  |  | 385 | 173 | 45 | 50181142 | 63180059.12 | Delayed | delayed
248 | Housing_Project_248 | Kisumu | 3 | 2 | 2023-12-31 | 2025-11-10 | 2026-03-31 | 2026-03-16 | 437 | 437 | 100 | 95227370 | 119376103.74 | Completed | completed_after_extension
249 | Housing_Project_249 | Kisumu | 2 | 1 | 2024-04-28 | 2026-05-04 | 2026-10-08 | 2026-09-10 | 484 | 484 | 100 | 66323191 | 84112808.78 | Completed | completed_after_extension
250 | Housing_Project_250 | Kisumu | 4 | 1 | 2025-02-15 | 2025-11-02 |  | 2025-10-22 | 532 | 532 | 100 | 108043078 | 84220744.31 | Completed | completed_on_time